## Control
KITALE NATIONAL POLYTECHNIC
EVALUATION REPORT ON THE EFFECTIVENESS OF ACTIONS TAKEN TO ADDRESS RISK REGISTER AND OPPORTUNITY- INDUSTRIAL LIAISON OFFICE
Prepared: Industrial Liaison Officer Signature………………………………......
Date: 1st October 2021

## Risk Register
SNO. | PROCESS | INTERESTED PARTIES & THEIR REQUIREMENTS | RISK DESCRIPTION | CAUSES | AREA OF IMPACT | RISK OWNER | IMPACT | LIKELIHOOD | RISK LEVEL | STRATEGY | EXISTING CONTROLS | ADDITIONAL CONTROLS | RESOURCES | TARGET DATE | RESIDUAL RISK |  |  | RESPONSIBILITY | REMARKS
[15 empty] | IMPACT | LIKELIHOOD | RISK LEVEL | ILO | Negligible cases reported
1 | Industrial attachment | Parents/Sponsors, Principal, Department, Insurance agency, Government[MOE] | accidents during attachment | poor maintenance of facilities, lack of proper orientation of trainees | Health | ILO | 3 | 1 | 3 | TRANSFER | ISSUE INSURANCE COVER | Cautioning and briefing students on need to take neccessry precautions | Funds, Protective gear | before trainees proceed for attachment | 3 | 1 | 3
2 | Industrial attachment | Department, industry, ILO | Trainee ending attachment after assessment before scheduled end | lack of :- integrity, financial support | REPUTATION | ILO | 1 | 4 | 4 | REDUCE | Delayed assessment | emphasise on need to complete attachment period during briefing. Insist on trainees submiting completion documents signed by industry supervisor. | none | Last month of attachment | 1 | 1 | 1 | ILO | very rare cases
3 | Attachment | Parents, Department, Principal, ILO. | Trainees Given duties not relevant to course | inadequate staff in industry, lack of integrity by supervisor rs | Regulatory | ILO | 1 | 5 | 5 | Reduce | Issue introduction letters specifying required areas of exposure | advicing trinees to see senior staff incase of misplacement for appropriate action. | none | before trainees proceed for attachment | 1 | 1 | 1 | ILO | no cases observed
4 | Attachment Assessment | Principal, Department, ILO, Industry | Assessors not going on assessment | lack of integrity and commitment to duty. | Legal | Principal | 2 | 4 | 8 | REDUCE | Submission of rubber stamped assessment tools, | Insist assessors submit transport receipts. | Assessment tools | two weeks after assessment | 1 | 1 | 1 | ILO | 100% assessment reported
5 | Attachment | ILO, Principal | non payment of attachment fees | economic factor | Regulatory | parent ,trainee | 2 | 4 | 8 | Reduce | denying logbooks to fee defaulters | trainees made to pay attachment fees before other fees | none | Before att. | 2 | 1 | 2 | ILO | The strategy has worked
6 | issuing of insuarance policies | industries, trainees, parents/sponsors and ILO | late processing of insuarance policies | delay in validating insuarance list and budgeting | Regulatory | ILO/ finance | 1 | 3 | 3 | avoid | observe budget deadlines | timely handing in of lists of attachees | finances | 1 term | 1 | 1 | 1 | ILO | timely issuance of covers observed
7 | Budget making | Ilo ,department | feedback from attaches on placement Late or no FEEDBACK | Late placement, Lack of understa nding of trainees | s | ILO | 3 | 4 | 12 | REDUCE | observe reporting dateline | Providing DACs with airtime to contact trainees | finances | 3rd week of period | 3 | 2 | 6 | more measures to be implemented | airtime to be provide
8 | Atttachment | industry ,polytechnic | indispline | indispline cases |  | Principal | 1 | 3 | 3 | reduce | counselling of student at the deans office | involve parents. Spell out disciplinary measures. | none | none | 1 | 1 | 1 | no cases reported | rules and regulations to be adheared to
9 | Attachment | parent ,principal,ILO | sexual harassement on attachment | lack of integrity by officer | legal | ILO,HOD | 2 | 2 | 4 | REDUCE | students to be advised to report cases to the senior managers in the industry | students to be mature and responsible | none | none | 2 | 2 | 4 | no cases reported | trainees should report such cases
10 | Attachment | trainee | inadequate funds while on attachment | economic factor | operational | parent ,trainee | 1 | 4 | 4 | reduce | advise parent to provide enough money for upkeep | trainee to be responsible and operate within the resources provided by parent or guardian | none | none | 1 | 1 | 1 | no cases reported | trainees to ensure they have enough money
11 | Attachment | parent ,principal,ILO ,industry | students going on attachment in insecure ,unsafe places | Insecure and limited attachment places | safety and security | trainee | 1 | 2 | 2 | reduce | Advice trainees to avoid unsafe places and to get in touch with security personel in areas of attachment | none | none | none | 1 | 2 | 2 | no cases reported | students adviced to avoid insecure places
12 | Attachment | parent, principal ,ILO, industry | incomplete attachment due to industrial unrest and strikes | instability in the industry | operational | trainee | 2 | 3 | 6 | reduce | advise students to look for alternative placements | none | NONE | NONE | 1
[7 empty] | 2 | 4
[7 empty] | 1 | 5

## Opportunities Assessment
OPPORTUNITIES ASSESSMENT
# | ISSUES | OPPORTUNITIES | ACTION | RESOURCES | TIMELINES | RESPONSIBILITY | STATUS | COMMENTS
1 | Inadequate attachment places | establish production units in polytechnic whre some trainees can be attached | liase with principal to encourage departments to establish P.Us | finances, facilities and policies | within the finacial year | PU coodinator and committee | no ongoing PU's | PU's need to be urgently established